## Risk Matrix
Current Situation
Likelihood | Likely |  | 2 | 1 3 4
Occasionally
Rarely
|  | Low | Medium | High
Impact
After Implementation of Framework
Likelihood | Likely
| Occasionally | 1 4 | 3
| Rarely | 2
|  | Low | Medium | High
Impact

## Risk Details
|  |  | Current |  |  | Post Mitigation
Risk Number | Risk | Details | Likelihood | Impact | Mitigation | likellihood | Impact
Example 1 | The team does not have a consistent, structured framework for the development of new/early career support workers with minimal training in place. | Support workers may find it difficult to develop their skills as they do not have a clear framework for their development. As a result, they are lacking in opportunities to follow a richer and more rewarding career pathway. This could result in poor motivation and staff retention and recruitment issues. | Likely | High | Implementation of the RCSLT support worker framework creates the structured framework needed for support workers to have full sight of their development and career pathway. | Occasionally | Low
Example 2 | There is no CPD process for support workers. | Support workers have no way of identifying where their level of expertise currently lies or the gaps in their current competencies. As a result, the service cannot maximise the use of experienced support workers or identify where there may be risk within the scope of practice. | Likely | Medium | Implementation of the RCSLT support worker framework helps the service to recognise the support worker's areas of skill and areas needing improvement. This allows the service to continually develop even experienced support workers, and reduce any risks to the service from support workers working outside the scope of their role | Rarely | Low
Example 3 | Perceived lack of SLT time to provide consistent supervision and oversight of support workers. | SLT's may perceive a lack of time to supervise and assist support workers development through supervision/CPD. This can result in a number of risks relating to support workers including: lack of motivation, retention issues or working outside of the scope of their role. | Likely | High | Implementation of the RCSLT support worker framework provides SLT's with a clear site of the benefits of developing support workers. This includes increased confidence in the role of the support worker and reducing risks to the service. | Occasionally | Medium
Example 4 | Lack of delegation to support workers. | SLT's may be reticent in delegating additional responsibilities to support workers as they do not have a framework to give them confidence in the ability of the support worker to take on these responsibilities. This results in missed opportunities for easing the workload of the SLT, as well as in service development. | Likely | High | The support worker framework provides the SLT with a clear view of the current skillset of support workers. The framework allows for delegation of additional responsibilities as the support workers skill and competencies increase, helps SLTs understand the benefits of helping support workers to develop, and ultimately helps the SLT with caseload management and in service development. | Occasionally | Low
5
6
7
8
9
10